## Professional Meeting Notes

### Meeting Topic

Planning and Organization of the Technical Workshop

### Key Discussion Points

- A technical workshop will be organized next month.

- An industry expert will be invited as the guest speaker.

- The proposed workshop date is November 15.

- The seminar hall was proposed as the venue.

- A registration form needs to be prepared for participants.

- All workshop arrangements should be finalized by November 5.

### Decisions Made

| Item | Decision |
| --- | --- |
| Workshop | Technical workshop |
| Speaker | Industry expert |
| Proposed Date | November 15 |
| Venue | Seminar Hall |
| Finalization Deadline | November 5 |

Action Items

| Action Item | Responsible Person | Deadline |
| --- | --- | --- |
| Contact and invite the industry expert | Student 2 | Before November 5 |
| Prepare the registration form | Student 3 | Before November 5 |
| Finalize all workshop arrangements | Student 1, Student 2 & Student 3 | November 5 |